## Sheet1
Task | Start Date | End Date | Importance | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14
Project Proposal | Week 1 | Week 2 | 1- (Normal) | Week 1: Project Proposal
Python Upgrade to 3.9 | Week 3 | Week 5 | 3 - (Critical) | Week 3: Python Upgrade to 3.9
Requirements Specification Document [Initial] | Week 4 | Week 5 | 1- (Normal) | Week 4: Requirements Specification Document
Rpy2 Removal | Week 6 | Week 9 | 2 - (Important) | Week 6: Rpy2 Removal
Software Development Plan [Initial] | Week 6 | Week 7 | 1- (Normal) | Week 6: Software Development plan
Python Upgrade to 3.10 or 3.11 | Week 10 | Week 11 | 2 - (Important) | Week 10: Python Upgrade to 3.10 or 3.11
Software Development Plan [Update] | Week 11 | Week 12 | 1- (Normal) | Week 11: Software Development Plan
Requirements Specification Document [Update] | Week 12 | Week 13 | 1- (Normal) | Week 12: Requirements Specification Document
PDF Dependency Replacement | Week 12 | Week 14 | 3 - (Critical) | Week 12: PDF Dependency Replacement